## Project Plan
Project: | Project Name | Start Date: |  |  | 2015-06-22
Provider: | Test Provider | Completion Date: |  |  | 2015-06-24
Collabrance Onboarding Project Plan | [5 empty] | 2015-06-22 |  |  |  |  | 2015-06-29 |  |  |  |  | 2015-07-06 |  |  |  |  | 2015-07-13 |  |  |  |  | 2015-07-20 |  |  |  |  | 2015-07-27 |  |  |  |  | 2015-08-03 |  |  |  |  | 2015-08-10 |  |  |  |  | 2015-08-17 |  |  |  |  | 2015-08-24 |  |  |  |  | 2015-08-31
Activity / Task Name |  | Assigned To | Days | Start Date | Finish Date | time axis 2015-06-22 to 2015-09-04
Project Duration |  |  |  | 2015-06-22 | 2015-06-24 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre Implementation Call |  |  | #REF! | 2015-06-22 | 2015-06-22 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subscriber Information Tasks |  |  | 4 | 2015-01-22 | 2015-01-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete Configuration Form |  | Test Provider | 2 | 2015-01-22 | 2015-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review Configuration Form |  | Collabrance | 1 | 2015-01-26 | 2015-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Provide Clarifications |  | Test Provider | 1 | 2015-01-27 | 2015-01-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Configuration Form Acceptance |  | Collabrance | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Infrastructure Tasks |  |  | 6 | 2014-12-15 | 2015-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fortinet - UTM |  |  | 3 | 2014-12-25 | 2015-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre Configuration |  | Collabrance | 1 | 2014-12-25 | 2014-12-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delivery - UTM |  | Test Provider | 1 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Onsite Configuration |  | Both | 1 | 2015-01-08 | 2015-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data Protection |  |  | 2 | 2014-12-15 | 2015-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order Data Protection - BDR |  | Collabrance | 1 | 2014-12-15 | 2014-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delivery - Data Protection - BDR |  | Test Provider | 1 | 2015-01-06 | 2015-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Configuration Data Protection - BDR |  | Collabrance |  | 2015-01-06 | 2015-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Configuration Data Protection - File Based |  | Collabrance |  | 2015-01-06 | 2015-01-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Hardware |  |  |  | 2015-06-22 | 2015-06-23 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Order New Hardware |  | Test Provider | 2 | 2015-06-22 | 2015-06-23 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stage Hardware |  | Test Provider | 2 | 2015-06-22 | 2015-06-23 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deploy Hardware |  | Test Provider | 2 | 2015-06-22 | 2015-06-23 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RMM Stabilization Tasks |  |  | 7 | 2015-01-07 | 2015-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uninstall AV |  | Test Provider | 1 | 2015-01-07 | 2015-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Install N-able Agent |  | Test Provider | 1 | 2015-01-07 | 2015-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Install AV Defender |  | Test Provider | 1 | 2015-01-07 | 2015-01-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete Stabilization (Servers & Workstations |  | Test Provider | 3 | 2015-01-07 | 2015-01-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Verify All Stabilization Work |  | Collabrance | 1 | 2015-01-12 | 2015-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hosted Email Tasks |  |  |  | 2015-01-05 | 2015-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create Account and Mailboxes |  | Collabrance |  | 2015-01-05 | 2015-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Complete Data Migration |  | Collabrance |  | 2015-01-14 | 2015-01-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mail Cutover |  | Collabrance |  | 2015-01-15 | 2015-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Account Configuration (Additional Services) |  | Collabrance |  | 2015-01-15 | 2015-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subscriber Orientation |  |  |  | 2015-01-09 | 2015-06-24 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service Orientation Meeting |  | Test Provider |  | 2015-01-09 | 2015-06-24 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service Activation |  | Test Provider |  | 2015-01-15 | 2015-06-24 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Delay - Schedule Change |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Subscriber Information
Subscriber Information
1 | Service Activation team uploads configuration form to the Collabrance InfoZone partner portal
2 | Service Provider completes and submit configuration form
3 | Service Activation team reviews configuration form
4 | Service Activation team requests configuration form clarifications
5 | Service Provider submits clarifications
6 | Service Activation team approves configuration form

## New Hardware
RMM Detailed Installation Tasks
1 | Order new hardware
2 | Service Provider receives and configures hardware
3 | Service provider deploys new hardware

## UTM
UTM - Detailed Installation Tasks
1 | Service provider completes the Fortinet - UTM section on the configuration from
3 | Service Activation team reviews configuration form and requests clarifications if necessary
3 | UTM device is pre configured by Service Activation team in their Cedar Rapids office
4 | UTM device is shipped to the Service Provider’s main location
5 | Service Provider informs Collabrance when the UTM has been received
6 | Service Activation team schedules a date with the Service Provider to complete the on-site implementation process
7 | Service Provider’s technician disconnects existing UTM/firewall and connects new UTM
8 | Service Activation team completes all on-site configuration tasks
* VPN activated
* Internal Wi-Fi activated
* Guest Wi-Fi activated
* VPN tunnel created
9 | Service Provider’s technician distributes VPN client to any user who requires remote VPN access to the network.

## Data Protection - BDR
Data Protection - BDR Detailed Installation Tasks
1 | The BDR appliance will be ordered by the Service Activation team after the pre implementation meeting.
2 | The BDR appliance will be shipped to the Service Provider’s main location.
3 | Each device that will be managed by the BDR must be identified on the data protection section of the configuration from
4 | The Service Provider notifies the Service Activation team when the BDR appliance arrives
5 | The Service Activation team will schedule a date with the Service Provider to complete the on-site implementation process
6 | The Service Provider’s technician connects the BDR appliance to the subscriber’s network
7 | The Service Provider’s technician downloads BDR agent software and installs it on all the devices that will be managed by the BDR appliance. A reboot is necessary after the agent is installed.
8 | The Service Activation team will complete the BDR configuration
9 | The Service Activation Team will verify initial back-up completed successfully
10 | The Service Team will notify the Service Provider that back-up and verifications completed successfully
11 | The Service Activation team will determine if a round trip device is required for moving the initial data seed to the Datto data center
12 | The Service Provider’s technician will be responsible of attaching the round trip device, disconnecting it and shipping it to the data center. Shipping labels and directions are provided with the device.
13 | The Collabrance NOC will begin to manage and monitor all BDR operations

## Data Protection - File Level
Data Protection - File Level Detailed Installation Tasks
1 | The file folders that will be included in the back-up must be identified on the data protection section of the configuration from
2 | The Service Activation team will schedule a date with the Service Provider to complete the on-site implementation process
3 | The Service Activation team will install an agent on each device that is to be backed-up
4 | The Service Activation team will configure the back-up configuration for each device
5 | The NOC will begin to manage and monitor all back-up operations

## RMM
RMM Detailed Installation Tasks
1 | Per covered device
Uninstall existing AV
Install N-able agent
Install Collabrance supported AV
Complete stabilization tasks outlined in the hardware inventory report
· Minimum 80% free disk space
· Supported OS
· Minimum RAM for installed OS
· Proper service pack
2 | Service Activation team confirms that all devices meet stabilization criteria
3 | All managed derives and users are identified on the configuration form. All devices identified in N-able should be include on the managed devices list.
4 | Service Activation team and Service Provider set service activation date

## Hosted Mail
Hosted Email
1 | Service Provider completes the Hosted Exchange section on the configuration form
2 | The Service Activation team will review the configuration form and access the current mail solution(s) to determine the best process for accomplishing the migration to Hosted Exchange.
3 | Based on the Service Activation team's review the Service Provider might be required to collect additional information regarding the existing mail solution and its configuration.
4 | The Service Activation team will formulate a migration plan
* Exchange to Exchange Migration: Migrating from On-Premise Exchange or Hosted Exchange
* Manual PST Migration: Migrating from any Hosted POP/IMAP and sometimes due to certain circumstances a Hosted or On-Premise Exchange environment requires a manual PST migration
5 | Service Provider will communicate migration plan to the subscriber
6 | The Service Activation team creates Active Directory objects and relationships in the Intermedia Hosted Exchange account according to the subscriber’s Migration Plan.
7 | During a project where Exchange to Exchange migration is being competed, the Service Activation team changes the mail routing on the Intermedia Hosted Exchange account to deliver mail to the current Exchange server (Mail Forward Redirect)
8 | The Service Provider verifies that the account configuration has been imported correctly. The migration will not proceed until this has been verified that the data is correct
9 | The Service Provider provides the Service Activation team with a final cutover date for when the users will begin using their new mailboxes.
10 | The Service Activation team (or Service Provider) will change the MX records for the domain to point to Intermedia’s servers. The TTL must expire for DNS propagation to proceed with the next step
11 | Outlook Anywhere is required to be functional before proceeding forward wish the migration . If it is not functional, it must be configured.
12 | Before the planned cutover date, the subscriber’s mailbox data will be exported from their existing Exchange mailboxes and imported into their Hosted Exchange account using RPC over HTTP. The time for this to complete is determined by the volume of data, connection speed, and access to your current Exchange server.
13 | The Service Provider will verify that the mailbox data has copied correctly to the new account. Once this has been verified the migration will proceed.
14 | The Service Activation team and/or the Service Provider will configure profiles on the Outlook clients to connect to the new Hosted Exchange account.
15 | If a manual PST migration is required the Service Activation team and Service Provider will select the best export and delivery options for moving the PST mailbox data
16 | To cutover a new account the Service Activation team will
* Change mail routing to stop forwarding mail through Intermedia and instead retain mail and make available through new hosted solution.
* Create an Auto discover CNAME record for your domain
* Configure all your clients and devices to connect to the new server.
* Export and import public folder data via Outlook
17 | The Service Activation team will copy a differential of mailbox data from the current Exchange server, if data has been moved using RPC. If mail is stored anywhere other than on the Exchange server, the Service Provider will be responsible for data migration of incremental mail.
18 | The Service Activation team will verify that the data has copied correctly
19 | The Service Provider will need to configure optional add-ons such as mobile devices (ActiveSync), Lync, message encryption, message archiving, etc.
20 | The Service Activation team and Service Provider will work together to determine if the migration is 100% complete. Once both parties are agreed the migration is complete, the onboarding case will be closed and your account will be marked as in production.

## Subscriber Orientation
Subscriber Orientation
1 | Service Activation team and Service Provider set service activation date
2 | Service Provider performs service orientation session with the subscriber's personnel
* Welcome sheet overview
* Review policies and procedures
* Make demonstration call with Service Desk
3 | Service Desk made available to the subscriber's users and all remote monitoring services activated